## 0000
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Estimation | Notes | Date started (or planned) | Date finished (or planned)
TA-01 | Register Account | As a TA, I want to register an account using my unique student ID, so that I can access the TA recruitment system and complete all application-related operations. | Must Have | 1 | 1. Student ID is validated for uniqueness against system storage files. 2. Password must be at least 8 characters with a mix of letters and numbers. 3. All registration data is saved to a JSON/CSV text file without database usage. 4. Clear, user-friendly error message is displayed for duplicate student ID registration. 5. Successful registration redirects the user to the login page automatically. | 3 | Core authentication foundation; adheres to mandatory text file storage rule | 3/23/26 | 3/29/26
TA-02 | Login to System | As a TA, I want to log in with my student ID and password, so that I can access my personalized TA dashboard and manage my profile and applications. | Must Have | 1 | 1. Exact student ID and password match is required for successful login. 2. Generic error message is shown for invalid credentials to prevent user enumeration. 3. User session persists until manual logout or system closure. 4. Re-verification is required for sensitive actions (e.g., changing personal information). 5. Successful login redirects to the TA personalized dashboard. | 2 | Security baseline for the system; session management core | 3/23/26 | 3/29/26
TA-03 | Manage Personal Profile | As a TA, I want to edit my personal information (email, phone, major), so that my profile information is always up-to-date for MO review. | Must Have | 1 | 1. Editable fields include email address, phone number, and academic major; student ID and full name are read-only. 2. Real-time input validation is applied (e.g., valid email format, numeric phone number). 3. All profile changes are saved to text file storage immediately and persist after logout. 4. A confirmation message is displayed for successful profile updates. 5. Profile data is linked to all future and past job applications. | 2 | Core profile management; data consistency with applications | 3/23/26 | 3/29/26
TA-04 | Upload CV Document | As a TA, I want to upload my CV file to the system, so that MOs can review my qualifications when I apply for TA jobs. | Must Have | 1 | 1. Supported file formats are PDF and Word; maximum file size is 5MB (configurable by Admin). 2. File is stored in a designated server directory, and the file path is saved to JSON/CSV data files. 3. Upload success displays the file name, size, and upload timestamp on the profile page. 4. Users can replace an existing CV with a new version, overwriting the old file path. 5. Clear error messages for unsupported formats or oversized files. | 3 | Core file handling feature; mandatory for job applications | 3/23/26 | 3/29/26
TA-05 | View Available TA Jobs | As a TA, I want to view all available TA job postings for the current semester in a clear list, so that I can browse all open roles and select those I am interested in. | Must Have | 1 | 1. All available TA jobs for the current semester are displayed in a single list, sorted by posting date (newest first). 2. Each job listing shows key details: title, module, required skills, application deadline, and remaining days until deadline. 3. Clicking a job listing opens the full job details page. 4. Expired/closed jobs are automatically excluded from the list. 5. A friendly "no open jobs available" message is shown if there are no active TA postings. | 2 | Basic job browsing feature; simplified as semester course volume is limited | 3/23/26 | 3/29/26
TA-06 | Apply for TA Jobs | As a TA, I want to submit applications for available TA jobs with one click, so that I can formally apply for roles I am interested in. | Must Have | 1 | 1. Application is only allowed if the TA has an uploaded CV in the system. 2. Duplicate applications for the same job are prevented with an error message. 3. Application data (TA ID, job ID, submission time) is saved to applications.json/CSV. 4. Application status defaults to "Submitted" and is visible on the TA dashboard. 5. A confirmation message is displayed for successful application submission. | 3 | Core business function; dependent on TA-04 (CV Upload) | 2026-04-06 | 2026-04-12
TA-07 | Receive In-App Notifications | As a TA, I want to receive in-app notifications for application status changes, so that I stay informed of my application progress in a timely manner. | Should Have | 2 | 1. A bell icon on the dashboard shows the count of unread notifications. 2. Notifications include job name, new application status, and status update timestamp. 3. Clicking a notification jumps directly to the corresponding application detail page. 4. Notifications are saved to notifications.json and can be marked as read/unread. 5. Notifications are triggered for all status changes (Shortlisted, Interviewed, Offered, Rejected). | 3 | Real-time progress updates; core user experience feature | 4/13/26 | 4/19/26
TA-08 | TA Application & Hiring Limit Enforcement | As a TA, I want the system to enforce application and hiring limits for TA roles, so that I can apply for a reasonable number of jobs while adhering to the school's maximum 3-course TA hiring rule. | Should Have | 2 | 1. A TA can submit a maximum of 5 job applications per semester (configurable via system parameters). 2. The system prevents a TA from being hired for more than 3 TA positions in the same semester. 3. A clear error message is displayed when a TA attempts to submit more than the maximum allowed applications. 4. The system blocks any status update to "Offered/Hired" if the TA has already reached the 3-course hiring limit. 5. The TA can view their current application count and hired course count on their dashboard. | 3 | Enforces school's TA workload policy; configurable limits via admin settings | 4/13/26 | 4/19/26
TA-09 | Submit Cover Letter with Application | As a TA, I want to add an optional cover letter when applying for a job, so that I can explain my motivation and suitability for the TA role to the MO. | Should Have | 2 | 1. A text area for cover letter is included in the job application form (500 character limit). 2. Cover letter content is saved and bound to the corresponding application record. 3. MOs can view the cover letter when accessing the full application details. 4. Cover letter can be edited before the job application deadline. 5. Character count is displayed in real-time while typing the cover letter. | 2 | Adds context to applications; improves MO evaluation accuracy | 4/13/26 | 4/19/26
TA-10 | View Application History | As a TA, I want to view my complete application history across all semesters, so that I can track my past TA application records and outcomes. | Should Have | 2 | 1. Application history lists all past and current applications with key details (job title, semester, status, final outcome). 2. Users can filter application history by academic semester. 3. Historical application data is read-only and stored in archived text files. 4. Final outcome (Hired/Not Hired) is clearly displayed for all completed applications. 5. Application history can be sorted by submission date (newest/oldest). | 3 | Long-term record tracking; supports TA career planning | 4/13/26 | 4/19/26
TA-11 | Export Profile as PDF | As a TA, I want to export my personal profile and CV link as a single PDF file, so that I can share my qualifications externally or for other applications. | Could Have | 3 | 1. A single "Export Profile" button generates a formatted PDF file. 2. PDF includes profile info (name, ID, major, contact), skill set, and a direct link to the uploaded CV. 3. Sensitive data (e.g., password hash) is excluded from the PDF. 4. PDF is downloaded directly to the user's local system. 5. PDF has a clean, professional layout suitable for formal review. | 5 | Value-added utility feature; offline profile access | 2026-04-20 | 2026-05-03
TA-12 | AI diagnoses CV and recommends jobs | As a TA applicant, I want to use an AI Diagnosis function, so that the AI can analyze my skills from my uploaded resume and recommend suitable TA positions for me to choose and apply. | Want Have | 4 | 1. The system displays an "AI Diagnosis" button on the TA applicant homepage. 2. The system reads and parses skill information from the uploaded CV. 3. The AI matches the applicant’s skills with open TA positions. 4. A list of recommended positions is shown with matching score and reason. 5. The applicant can click any recommended position to view details and apply directly. | 8 | Relying on the accuracy of TA resume content, the TA-02 (CV upload) function development needs to be completed first | 2026-05-04 | 5/17/26
TA-13 | Use AI to "Improve Yourself" | As a TA applicant, I want to use the AI-powered "Self-Improvement" function so that the system can analyze my resume and the jobs I have applied for, identify the skills I lack, and provide me with skill improvement directions, recommended learning content and learning methods for reference | Want Have | 4 | 1. The "Improve Yourself" function entry is located under the "AI Tools" module in the TA's personal center. 2. The system automatically reads the resume data (skills/experience fields) that the applicant has uploaded and the requirements (job conditions) of the applied positions. 3. AI outputs three core results: ① A list of missing skills (marking the degree of gap between skills and job requirements, such as "urgently need to be supplemented" or "suggested improvement") ② Skill improvement directions (such as "academic English writing → focusing on paper correction scenarios") ③ Learning recommendations (including specific resources: such as MOOC links and textbook names; learning methods: such as "two simulated correction exercises per week") 4. Supports the "Save Learning Plans" function, which can be viewed at any time in the personal center. 5. Supports the "Reanalysis" function (suggestions can be regenerated after updating the resume/adding new job applications). 6. Learning resource links are direct and there are no invalid links. | 13 | It is necessary to simultaneously read the structured data of resumes and applied positions. | 2026-05-04 | 5/17/26
MO-01 | MO Account Registration & Approval | As an MO, I want to register an account for the system, so that I can post TA recruitment jobs and review applications (Admin approval required). | Must Have | 1 | 1. MO registration includes faculty ID, name, department, and module information. 2. Registration status defaults to "Pending" and is sent to Admin for approval. 3. MO can only log in and post jobs after Admin approves the account. 4. Rejected MO registration includes a written reason and is notified to the applicant. 5. All MO registration data is saved to mo_registrations.json/CSV. | 3 | Core MO access control; prevents unauthorized job posting | 3/23/26 | 3/29/26
MO-02 | Post TA Recruitment Jobs | As an MO, I want to post new TA recruitment jobs to the system, so that I can recruit qualified students for my module's TA roles. | Must Have | 1 | 1. Job posting form includes title, detailed description, required skills, module association, and application deadline. 2. Jobs are automatically associated with the MO's module and faculty ID. 3. All job data is saved to jobs.json/CSV (no database usage). 4. Posted jobs are immediately visible to TAs if the deadline is not expired. 5. MO can preview the job posting before formal publication. | 5 | Core MO business function; foundation of the recruitment system | 3/23/26 | 2026-04-05
MO-03 | Set & Manage Application Deadlines | As an MO, I want to set and edit application deadlines for posted jobs, so that applications close automatically after the specified date. | Must Have | 1 | 1. Date picker interface prevents selecting past dates for new job deadlines. 2. Expired jobs are marked "Closed" and are not available for TA applications. 3. MO can extend the deadline of a job before the original deadline passes. 4. System checks job expiry status daily and updates status in text files. 5. Deadline is prominently displayed on all job listings for TAs. | 2 | Time management for recruitment; ensures application cutoff | 2026-04-06 | 2026-04-12
MO-04 | View Job Applications | As an MO, I want to view all applications for the jobs I posted, so that I can screen and evaluate TA applicants. | Must Have | 1 | 1. Application list shows TA name, student ID, major, CV link, and submission time. 2. List can be sorted by submission time (newest/oldest) or major. 3. Clicking an application opens the full details (profile, CV, cover letter if applicable). 4. The system only displays applications for the MO's own posted jobs. 5. Application list is filtered to exclude canceled/expired applications. | 3 | Core MO evaluation function; dependent on MO-02 and TA-06 | 2026-04-06 | 2026-04-12
MO-05 | Update Application Status | As an MO, I want to update the status of TA applications, so that TAs are informed of their evaluation progress and outcomes. | Must Have | 1 | 1. Status options include Submitted, Shortlisted, Interviewed, Offered, and Rejected. 2. Only valid state transitions are allowed (e.g., Submitted → Shortlisted, not Rejected → Offered). 3. Status changes trigger an in-app notification for the TA (TA-08). 4. All status change history is saved with timestamps to the application record. 5. MO can add a short note when changing the status to Rejected/Offered. | 3 | Core evaluation workflow; real-time progress communication | 2026-04-06 | 2026-04-12
MO-06 | Add Private Interview Notes | As an MO, I want to add private interview notes for TA applicants, so that I can record evaluation details and remember key points during the selection process. | Should Have | 2 | 1. Notes field is visible **only** to the MO who created the application review. 2. Notes support multiple edits and updates with no character limit. 3. Last updated timestamp and MO ID are attached to all notes. 4. Notes are saved and stored with the corresponding application record in text files. 5. Notes can be searched for key words within the MO's own application list. | 2 | MO evaluation support; improves selection consistency | 4/13/26 | 4/19/26
MO-07 | View Eligible TA Candidates & Send Invitations | As an MO, I want to view a list of eligible TAs who have not been hired for the maximum 3 courses in the current semester, so that I can send targeted recruitment invitations for my underfilled TA positions. | Should Have | 2 | 1. MO can access a list of all active TA accounts that have not reached the 3-course hiring limit for the current semester. 2. The list displays TA key details: student ID, name, major, uploaded CV link, current hired course count, and contact information. 3. MO can filter the candidate list by academic major and required skill tags for the target job. 4. MO can send in-app recruitment invitations to selected candidates, with the job details and a direct link to the application page. 5. Sent invitations are logged with timestamps, and candidates receive an in-app notification for the invitation. | 3 | Supports recruitment for underfilled positions; improves TA job matching efficiency | 4/13/26 | 4/19/26
MO-08 | Duplicate Past Job Postings | As an MO, I want to duplicate my past TA job postings, so that I can save time posting recurring jobs for my module. | Could Have | 3 | 1. MO can select any past job posting from their job history to duplicate. 2. Duplication generates a new job draft with all original details (title, skills, description). 3. Draft clears all date fields (deadline, posting date) for manual re-entry. 4. MO can edit the draft before formal publication to the system. 5. Duplicated jobs are marked with a "Duplicated from [original job ID]" note. | 3 | MO efficiency feature; reduces repetitive data entry | 2026-04-20 | 2026-05-03
MO-09 | View AI-Powered Skill Comparing candidates | As an MO, I want to use AI-generated skill to select two or more TA candidates so that the system can analyze and compare these candidates based on their resumes, providing reference analysis for my recruitment selection | Want Have | 4 | 1. MO has a "Select Candidates" checkbox on the candidate list page, which supports selecting two or more candidates. 2. After checking the box, the "AI Comparison" button will appear; clicking it will trigger the function. 3. AI can compare resume skills matching (with job requirements), relevant teaching experience, and professional background fit from three core dimensions. 4. Generate a visual comparison report (including dimensional scores and a summary of strengths and weaknesses). 5. The report supports online viewing and can be exported as a PDF. 6. Supports the "Reselect Candidates" function, triggering AI comparison a second time. | 13 | Relying on the accuracy of TA resume content, the TA-02 (CV upload) function development needs to be completed first | 2026-05-04 | 5/17/26
ADM-01 | Approve TA&MO Account Registrations | As an Admin, I want to review and approve/reject TA&MO account registration requests, so that only authorized faculty can post TA jobs on the system. | Must Have | 1 | 1. Admin views a pending approval list with all MO registration details (faculty ID, department, module). 2. Admin can approve or reject each request with a written reason for rejection. 3. Approved MO accounts are activated immediately and the MO is notified via in-app message. 4. All approval/rejection actions are logged to audit_log.txt with timestamp and Admin ID. 5. Pending requests are sorted by submission date (newest/oldest) for efficient review. | 3 | Core Admin access control; critical for system security | 3/23/26 | 3/29/26
ADM-02 | Manage All User Accounts | As an Admin, I want to manage all TA and MO user accounts, so that I can maintain system security and control access to the recruitment system. | Must Have | 1 | 1. Admin can enable/disable any TA or MO account with a single action. 2. Admin can reset the password of any user account, with a temporary password sent to the user's contact. 3. All account management operations are logged to audit_log.txt with timestamp and Admin ID. 4. Admin supports batch enable/disable operations for multiple accounts. 5. Disabled accounts prevent login and access to all system features. | 5 | Core Admin security function; system access control | 2026-04-06 | 2026-04-12
ADM-03 | Configure System Parameters | As an Admin, I want to configure key system parameters, so that the system can adapt to the school's changing recruitment policies and requirements. | Should Have | 2 | 1. Admin can read/write system parameters to a dedicated config.json file. 2. Configurable parameters include max CV file size, max TA weekly workload hours, allowed file formats, max TA applications per semester, and max TA hired courses per semester. 3. Parameter changes take effect immediately without system restart. 4. Invalid input values are intercepted with clear error messages (e.g., "Max file size cannot be 0"). 5. All parameter changes are logged to the audit log with timestamp. | 3 | System adaptability; core Admin configuration feature | 4/13/26 | 4/19/26
ADM-04 | Generate Recruitment Statistics Reports | As an Admin, I want to generate semesterly recruitment statistics reports, so that I can analyze hiring trends and provide data for the school's academic management. | Want Have | 4 | 1. Reports include key metrics: total jobs posted, total applications received, hire rate, module distribution, and applicant major distribution. 2. Reports can be filtered by academic semester, department, and module. 3. Reports support export to CSV format for further analysis. 4. Simple text-based data visualization (e.g., percentage breakdowns) is included in the report. 5. Only aggregated, non-identifiable data is included to protect user privacy. | 5 | Admin data analysis feature; supports school decision-making | 2026-05-04 | 5/17/26
ADM-05 | Use AI to balance TA workloads | As an admin, I want to use the "AI Workload Balancing" function so that the system can analyze the current workload of all TAs and provide reasonable TA allocation suggestions for new courses, avoiding TA overload and realizing fair and efficient resource allocation | Want Have | 4 | 1. There is an "AI Workload Balancing" function entrance in the Admin background 2. The system can automatically read the existing workload data of TA (number of assigned courses, weekly duration, task type) 3. Support the need for teaching assistants to enter new courses (number of people, required hours per week) 4. The AI generates 3 types of results: (1) Current overloaded TA list (2) Recommended priority list of idle TAs (3) Optimal allocation scheme (including workload estimate) 5. Visualize the results in "Workload Heat Map + Data Table" 6. Support exporting assignment proposal report (PDF format) 7. Save the final assignment after manually adjusting the AI suggestions | 13 | After the AD-01 (Admin View TA Workload) function is completed, the new job requirements data released by the MO must be obtained synchronously | 2026-05-04 | 5/17/26
SYS-01 | Enforce Text File Storage Compliance | As a Developer, I need the system to store all data exclusively in text files, so that I meet the course's mandatory technical requirement (no database usage). | Must Have | 1 | 1. No relational/non-relational databases (MySQL, SQLite, MongoDB, etc.) are used in any system component. 2. All system data is stored in JSON/CSV text files with consistent naming and structure. 3. File locking is implemented to prevent concurrent data write conflicts. 4. Automatic daily backups of all text data files are created in a dedicated backup directory. 5. Data file integrity is checked on system startup with error messages for corrupted files. | 8 | Mandatory course technical constraint; system foundation | 2026-04-06 | 2026-04-12
SYS-02 | Implement Robust Input Validation & Security | As a System Admin, I want the system to enforce strict input validation and security measures, so that the system is protected from malicious inputs and data breaches. | Must Have | 1 | 1. Server-side input validation is applied to **all** user inputs (no client-side only validation). 2. Path Traversal attacks are prevented in the file upload module (TA-04). 3. User passwords are stored as hashed values (no plain text) in text files. 4. Error messages do not leak system details (e.g., file paths, storage structure). 5. All user inputs are sanitized to prevent cross-site scripting (XSS) and injection attacks. | 5 | Mandatory security baseline; protects system and user data | 2026-04-06 | 2026-04-12